## Read me
Event + partnerships ops kit · sample
Made by Durva Thakkar for Clio's Strategic Engagement team · durvathakkar.com/clio
What this is | A ready-to-use ops workbook for one flagship event and the partner program around it. Works in Excel and Google Sheets.
Sample data | Every vendor, amount, name and date here is sample data I created to show the system. Nothing is Clio data.
Event date | Change 'Logistics'!C3 and every due date and 'days left' recalculates.
Colour key | Light blue cells are inputs. Everything else is a formula.
Tabs | Logistics · Vendors · Budget + reconciliation · Travel · Shipping · Volunteers · Comms calendar · Partner onboarding · Status + risks · AI workflow log

## Logistics
Logistics tracker · flagship conference (sample)
Due date = event date minus days before. Days left updates every time you open the file.
| Event date | 2026-10-26
# | Workstream | Task | Owner | Days before event | Due date | Days left | Status | Notes
1 | Vendors | Onboard AV vendor (tax form, banking, insurance certificate) | Coordinator | 45 |  |  | Done
2 | Vendors | Create PO for AV and staging | Coordinator | 40 |  |  | Done | PO approved
3 | Contracts | Contract signed with catering for partner dinner | Program manager | 35 |  |  | Done
4 | Swag | Order swag: notebooks, pens, stickers (quantity = registrations x 1.1) | Coordinator | 30 |  |  | Done
5 | Shipping | Ship booth kit to venue advance warehouse | Coordinator | 14 |  |  | In progress | Check the venue's receiving window
6 | Travel | Book team flights and hotel block | Coordinator | 21 |  |  | Done
7 | Speakers | Collect final speaker slides and bios | Program manager | 10 |  |  | In progress | 8 of 40 outstanding
8 | Sponsors | Confirm sponsor booth assets and logo files | Partnerships | 10 |  |  | Waiting | 2 sponsors pending
9 | Volunteers | Volunteer roster final + briefing deck sent | Coordinator | 7 |  |  | Not started
10 | Payments | Process deposits and local vendor payments | Coordinator | 7 |  |  | In progress
11 | Onsite | Print signage and badge stock | Coordinator | 5 |  |  | Not started
12 | Wrap-up | Expense reconciliation and post-event report | Coordinator | -7 |  |  | Not started | Due 7 days after
Progress
Formulas:
Days left = [Due date]-TODAY()

## Vendors
New vendor onboarding
Nothing gets a PO until every column is Yes.
Vendor | Service | Tax form | Banking info | Insurance cert | Contract | PO # | Ready to pay?
Northside AV | Audio visual | Yes | Yes | Yes | Yes | PO-2611
Harbour Catering | Partner dinner | Yes | Yes | No | Yes | PO-2614
Print Lab | Signage + badges | Yes | No | Yes | No
Swag Supply Co. | Branded swag | Yes | Yes | Yes | Yes | PO-2602

## Budget + reconciliation
Budget and expense reconciliation (sample figures, USD)
Variance over 5% or a missing receipt gets flagged before month-end close.
Line | Vendor | Budget | PO amount | Invoiced | Paid | Receipt on file? | Variance vs budget | Flag
Audio visual | Northside AV | 18000 | 18000 | 18450 | 18450 | Yes
Partner dinner | Harbour Catering | 12000 | 12000 | 12900 | 6000 | Yes
Swag | Swag Supply Co. | 9000 | 8600 | 8600 | 8600 | Yes
Signage + badges | Print Lab | 4000 | 0 | 0 | 0 | No
Team travel | Airlines + hotel | 22000 | 0 | 20750 | 20750 | No
Shipping | Freight | 3500 | 3500 | 3900 | 3900 | Yes
Total

## Travel
Team travel
One row per person. Keep confirmation numbers here, never in Slack.
Name | Role at event | From | Arrive | Depart | Flight booked | Hotel booked | Confirmation | Dietary / access needs
Team member A | Booth lead | YYZ | Oct 25 | Oct 28 | Yes | Yes | Sample-0001
Team member B | Speaker support | YVR | Oct 25 | Oct 28 | Yes | Yes | Sample-0002 | Vegetarian
Team member C | Partnerships | YYC | Oct 26 | Oct 28 | Yes | No
Team member D | Volunteer lead | YYZ | Oct 24 | Oct 28 | No | No

## Shipping
Shipping and swag
Ship to the venue's advance warehouse inside its receiving window. Track every box.
Item | Qty | Ship from | Ship to | Carrier | Tracking # | Ship by | Delivered?
Booth kit (3 cases) | 3 | Toronto office | Venue advance warehouse | Courier | SAMPLE-TRK-01 | Oct 12 | In transit
Swag: notebooks | 1200 | Supplier | Venue advance warehouse | Freight | SAMPLE-TRK-02 | Oct 9 | Delivered
Badge stock + lanyards | 1 | Print Lab | Venue | Courier |  | Oct 19 | Not shipped

## Volunteers
Volunteer roster
Each shift has a lead, a briefing and a backup.
Shift | Station | Time | Volunteers needed | Assigned | Gap | Lead
Day 1 AM | Registration desk | 7:00-11:00 | 6 | 6
Day 1 AM | Session room monitors | 8:30-12:30 | 8 | 6
Day 1 PM | Info desk | 12:00-17:00 | 3 | 3
Day 2 AM | Registration desk | 7:30-10:30 | 4 | 2
Day 2 PM | Expo hall guides | 12:00-16:00 | 4 | 4

## Comms calendar
Stakeholder comms calendar
Every email has an owner, an audience and a send date tied to the event date.
Audience | Email | Days before (+) / after (-) | Send date | Owner | Status
Speakers | Logistics pack: arrival, green room, AV check | 14 |  | Coordinator | Not started
Sponsors | Booth move-in times and asset deadline | 14 |  | Coordinator | Not started
Attendees | Know before you go | 7 |  | Coordinator | Not started
Volunteers | Shift confirmation + briefing deck | 7 |  | Coordinator | Not started
Speakers | Final reminder + day-of contact | 2 |  | Coordinator | Not started
Attendees | Day 1 morning: schedule + app | 0 |  | Coordinator | Not started
Attendees | Thank you + recordings | -2 |  | Coordinator | Not started
Sponsors | Leads + results recap | -5 |  | Coordinator | Not started
Volunteers | Thank you + feedback form | -3 |  | Coordinator | Not started

## Partner onboarding
Partner onboarding · first 30 days
Same steps for every new partner, so nothing depends on memory.
Day | Step | Owner | Done?
1 | Welcome email + kickoff call booked | Coordinator | No
2 | Partner record created, contacts and logo collected | Coordinator | No
5 | Kickoff call: goals, audience, first co-marketing idea | Partner manager | No
7 | Partner kit sent: brand rules, messaging, co-branding do's and don'ts | Coordinator | No
14 | Listing or landing page live | Partner manager | No
21 | First joint activity scheduled (webinar, post or event) | Partner manager | No
30 | 30-day check-in + first report | Coordinator | No

## Status + risks
Weekly status and risk log
Green = on track, Amber = at risk, Red = blocked. Every risk has an owner and a next step.
Workstream | Status | This week | Next week | Risk | Owner | Next step
Logistics | Green | Booth kit shipped, travel booked | Signage to print |  | Coordinator
Speakers | Amber | 32 of 40 slide decks in | Chase final 8 | Late slides delay AV prep | Program manager | Personal follow-up today, deadline Friday
Sponsors | Amber | 2 sponsors missing logo files | Assets locked | Signage reprint cost | Partnerships | Call both sponsors
Volunteers | Red | 4 shifts short | Fill gaps, send briefing | Registration line too long on Day 2 | Coordinator | Ask the team on Slack + backup list

## AI workflow log
AI workflow log
Every AI-assisted process: what it does, who checks it, and the time it saves (estimate, measured after 4 weeks).
Workflow | Tools | Input | AI step | Human review | Minutes before | Minutes after | Saved per week (est.) | Status
Receipts to reconciliation | Google Forms, Sheets, Gemini | Receipt photos | Read vendor, date, amount, category | Coordinator checks every line vs card statement | 90 | 25 |  | Testing
Speaker bios to session pages | Google Forms, Sheets, Gemini | Speaker form | Trim bios to 60 words, match style guide | Program manager approves each bio | 120 | 30 |  | Testing
Shared inbox triage | Gmail, Slack, Gemini | New emails | Label, priority, draft reply | Coordinator edits and sends | 150 | 60 |  | Testing
Post-event report | Sheets, Slides, Gemini | Survey + lead data | Summarize results and themes | Coordinator checks numbers vs source | 240 | 90 |  | Testing
Total