## Read me
Limina · Demand Gen months 1 to 6
By Durva Thakkar for Tyler Munro. Yellow cells are inputs. All numbers are SAMPLE targets to agree in month 1.
Tab | What it is | Who uses it
6-Month Roadmap | Theme, campaigns, deliverables and the number we watch, per month | Durva, Tyler
Weekly Calendar | 26 weeks of campaigns across webinars, email, ads, ABM, events, case studies | Durva, MDR
ABM Accounts | Tiered target accounts with an automatic account score and status | Durva + MDR (+ AEs)
Scoring Model | The signals and points behind the account score | Durva, MDR, Tyler
Buying Group + Messaging | Personas, what they care about, our message and proof | Everyone
ABM Plays | What we do at each stage, per tier, and who owns it | Durva, MDR
LinkedIn Ads | Campaigns, audiences, formats, budget split (formulas) | Durva, Tyler
Webinars | Monthly program with the T-minus run sheet | Durva
Event Playbook | T-60 to T+14 tasks for each event, with owners | Durva, MDR, Tyler
Case Studies | Pipeline from ask to published | Durva, CS, Sales
Rep Assets | Assets built for the MDR and AEs, and whether they get used | Durva, MDR
Hand-off Rules | The agreed rules between Demand Gen and the MDR | Durva, MDR, Tyler
KPI Dashboard | Monthly targets vs actuals, with conversion rates calculated | Tyler
UTM Builder | Builds tracked links for every campaign (formula) | Durva

## 6-Month Roadmap
Months 1 to 6
Sample dates assume a December start.
Month | Dates | Theme | Campaigns + work | Shipped | Number we watch | Status
1 | Dec 2026 | Learn + fix the plumbing | Shadow MDR + 5 sales calls; HubSpot audit; agree MQL + account score; Webinar #1 | Scoring live; hand-off rules; webinar run sheet; report v1 | Clean database + webinar #1 attendance | Not started
2 | Jan 2027 | Build the engine | Always-on LinkedIn (3 campaigns); nurture emails; ABM tier 1 + 2 lists; Webinar #2 | Ads live with UTMs; 5-email nurture; tier 1 briefs; case study #1 booked | MQLs per week | Not started
3 | Feb 2027 | Launch the ABM pilot | 10 account pages; account-named ads; case file mailer; MDR 1:1; Webinar #3; benchmark survey | Account pages; mailers; case study #1; industry one-pagers | Engaged tier 1 accounts | Not started
4 | Mar 2027 | Events season | Event #1 talk + booth; "See you at" ads; Toronto privacy dinner; Webinar #4 | Event page + meeting form; booth demo; cookies; 48-hr follow-up | Meetings booked at events | Not started
5 | Apr 2027 | Double down | Shift 20% budget to best channel; customer panel webinar; job-change play | Budget memo; panel webinar; case study #2; job-change alerts | Cost per meeting | Not started
6 | May 2027 | Prove it + plan H2 | Benchmark report; ABM pilot review; case study #3; H2 plan | Benchmark report; ABM results deck; case study #3; H2 plan | Pipeline sourced + influenced | Not started

## Weekly Calendar
26-week campaign calendar
Key weeks filled; blank weeks are build/optimise time. Edit freely.
Week | Week of | Webinar | Email / nurture | LinkedIn ads | ABM | Events | Case studies | Reporting
1 | Nov 30, 2026 | W#1 page + ads live | Welcome nurture set up | Awareness campaign live | Agree ICP + tiers | Shortlist 2 events | Ask CS for 5 customers | Report v1
2 | Dec 07, 2026
3 | Dec 14, 2026 | W#1 live + MDR follow-up | Webinar follow-up emails | Webinar ads | Tier 1 list (10) agreed | Speaking proposals | Interview #1 booked | Monthly report
4 | Dec 21, 2026
5 | Dec 28, 2026 | W#2 promo | Guide nurture | Thought leader ads | Account briefs | Event budget OK | Interview #1 | Weekly update
6 | Jan 04, 2027
7 | Jan 11, 2027
8 | Jan 18, 2027
9 | Jan 25, 2027 | W#3 promo | Benchmark survey email | ABM ads live | 10 account pages live | Event page live | Case study #1 published | Monthly report
10 | Feb 01, 2027
11 | Feb 08, 2027 | W#3 live | Survey reminder | Account-named ads | Case file mailers sent | "See you at" ads | Case #2 ask | Weekly update
12 | Feb 15, 2027
13 | Feb 22, 2027
14 | Mar 01, 2027
15 | Mar 08, 2027 | W#4 teardown | Event follow-up | Event burst | Dinner (Toronto) | Event #1 live | Interview #2 | Event report
16 | Mar 15, 2027
17 | Mar 22, 2027
18 | Mar 29, 2027
19 | Apr 05, 2027 | Panel webinar | Panel follow-up | Budget shift | Job-change play live | Event #2 prep | Case study #2 live | Monthly report
20 | Apr 12, 2027
21 | Apr 19, 2027
22 | Apr 26, 2027
23 | May 03, 2027 | W#6 benchmark results | Report promotion | Report ads | ABM pilot review | Event #2 | Interview #3 | H2 plan
24 | May 10, 2027
25 | May 17, 2027
26 | May 24, 2027

## ABM Accounts
ABM target accounts
SAMPLE accounts (not on Limina's public customer list). Tick signals with 1 or 0; score and status calculate.
Account | Industry | Country | Tier | Fit (20) | AI program (15) | 2+ visitors (15) | Pricing/security pages (15) | Guide (10) | Webinar (15) | Ad click (10) | Score | Status | Owner | Next step
Manulife | Insurance | Canada | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 0 |  |  | MDR | Account page + case file
Scotiabank | Banking | Canada | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 0 |  |  | MDR | Account page + case file
Sun Life | Insurance | Canada | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 |  |  | MDR | Account page + case file
TD Bank | Banking | Canada | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 |  |  | MDR | Account page + case file
BMO | Banking | Canada | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 0 |  |  | MDR | Account page + case file
Desjardins | Insurance / banking | Canada | 2 | 1 | 1 | 1 | 0 | 0 | 0 | 0 |  |  | Durva | Industry sequence
Great-West Lifeco | Insurance | Canada | 2 | 1 | 1 | 0 | 0 | 1 | 0 | 0 |  |  | Durva | Industry sequence
CIBC | Banking | Canada | 2 | 1 | 1 | 0 | 1 | 1 | 1 | 0 |  |  | Durva | Industry sequence
National Bank | Banking | Canada | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 |  |  | Durva | Industry sequence
Aviva Canada | Insurance | Canada | 2 | 1 | 1 | 0 | 1 | 0 | 1 | 0 |  |  | Durva | Industry sequence
Mount Sinai Health System | Healthcare | US | 2 | 1 | 1 | 0 | 1 | 0 | 0 | 0 |  |  | Durva | Industry sequence
Northwell Health | Healthcare | US | 2 | 1 | 1 | 1 | 0 | 1 | 1 | 0 |  |  | Durva | Industry sequence
Prudential Financial | Insurance | US | 3 | 1 | 1 | 1 | 0 | 0 | 0 | 0 |  |  | Durva | Webinar invites
Capital One | Banking | US | 3 | 1 | 0 | 0 | 1 | 1 | 1 | 0 |  |  | Durva | Webinar invites
Pfizer | Pharma | US | 3 | 1 | 1 | 1 | 1 | 1 | 0 | 0 |  |  | Durva | Webinar invites

## Scoring Model
Account score
Score out of 100. 60+ = hot (MDR this week). 35 to 59 = engaged. Under 35 = aware.
Signal | Points | Source | Why it matters
Fits ideal account (industry + 1,000+ staff) | 20 | Firmographics | Right kind of company
Active AI program or hiring AI roles | 15 | News, LinkedIn jobs | They have the problem now
2+ people visited the site this month | 15 | HubSpot / reverse IP | A buying group is forming
Visited pricing or security pages | 15 | HubSpot | Late-stage interest
Downloaded a guide | 10 | HubSpot form | Learning about the topic
Attended a webinar | 15 | Webinar platform | High intent, gave time
Clicked an account-named ad | 10 | LinkedIn | Responding to ABM

## Buying Group + Messaging
Buying group and message
Facts from getlimina.ai.
Persona | Cares about | Main message | Proof | Best channel
CPO / DPO | Audit, regulators, risk | Audit-ready outputs for HIPAA, GDPR, CPRA, PCI-DSS | Expert determination support | Webinars, guides, dinners
CISO | Where data goes | Runs in your VPC or on-prem, no third-party processing | Deployment + security pack | Security FAQ, MDR call
Head of Data / AI | Speed, data quality | Use your best data in AI, still useful after de-identification | 50+ entity types, 52 languages; 48 hrs to minutes (Boehringer Ingelheim) | Product tour, LinkedIn
Procurement / CFO | Cost, effort | Stop maintaining DIY scripts; running in days | Customer stories | AE, one-pagers

## ABM Plays
ABM plays by stage and tier
Owner: who does it.
Stage | Signal | Tier 1 (1:1) | Tier 2 (1:few) | Tier 3 (1:many) | Owner
Target | Fits ideal account | Account brief + personal page | Industry page | Webinar list | Durva
Aware | Ad impressions, visits | Account-named ads | Industry ads | Persona ads | Durva
Engaged | 2+ visitors, downloads | Case file mailer | Industry case study | Nurture email | Durva
Hot (60+) | Pricing page, webinar, repeat visits | MDR 1:1 + dinner invite | MDR sequence | Move up to tier 2 | MDR
Meeting | Discovery booked | AE + MDR call | AE call | AE call | MDR to AE
Opportunity | Use case + timeline confirmed | Marketing keeps buying group warm with proof | Same | Same | AE

## LinkedIn Ads
LinkedIn ads plan
Enter the monthly budget in B3 (yellow). Splits calculate.
Monthly budget (CAD): | 8000
Campaign | Audience | Format | Offer | Goal | Share | Monthly $
Always-on awareness | CPO, DPO, CISO, Head of AI · banks, insurers, health, pharma · 1,000+ | Thought leader ads, single image | Point of view | Reach buying group | 25%
Webinar + guide | Same + website retargeting | Lead gen forms, document ads | Webinar seat, guide | Leads + MQLs | 40%
ABM tier 1 + 2 | Matched account lists | Account-named image, conversation ads | Account page, data review | Engaged accounts | 25%
Event bursts | Event attendees + location | "See you at…" image | None | Booth visits | 10%
Total

## Webinars
Webinar program
Run sheet: T-28 page live · T-21 ads · T-14 MDR invites · T-7 reminder · T-1 reminder · T+1 recording + MDR calls.
# | Month | Topic | Audience | Speaker | Registrations (target) | Attended (target) | Attend rate | MQLs
1 | Dec | Governing every prompt (RAG + agents) | Privacy + AI | Patricia Thaine + customer (invited) | 150 | 60
2 | Jan | Audit-ready AI for HIPAA and GDPR | Privacy | Limina expert | 150 | 60
3 | Feb | Using call-centre data in AI, safely | Data + AI | Limina expert + partner | 150 | 60
4 | Mar | Live teardown: where PII hides in documents | Security + AI | Limina product | 150 | 60
5 | Apr | Customer panel: financial services | All | Customers (invited) | 200 | 80
6 | May | AI governance benchmark results | All | Patricia Thaine | 200 | 80

## Event Playbook
Event playbook
For each event. Example events: IAPP Global Privacy Summit, RSAC (dates TBC).
When | Task | Owner | Done?
T-60 | Pick 2 events with Tyler, submit speaking proposals | Durva + Tyler | No
T-60 | Build attendee target list (by tier) | Durva | No
T-30 | "See you at…" LinkedIn ads live (no CTA) | Durva | No
T-30 | Event page + meeting booking form | Durva | No
T-30 | MDR starts booking meetings | MDR | No
T-14 | Booth demo + 90-second talk track per persona | Durva + product | No
T-14 | Swag + [REDACTED] cookies ordered | Durva | No
T-14 | Booth briefing doc for everyone | Durva | No
Show | Badge scans tagged by tier, live posts | Durva + MDR | No
Show | Night-1 dinner for tier 1 guests | Tyler + AE | No
T+2 | Personal follow-up within 48 hrs | MDR | No
T+2 | Talk recording + slides to everyone scanned | Durva | No
T+14 | Report: meetings, pipeline, cost per meeting | Durva | No

## Case Studies
Case study pipeline
Goal (sample): 1 per quarter minimum, 3 by month 6.
Customer | Industry | Source (CS/Sales) | Stage | Interview date | Draft due | Approved | Published | Assets made
Customer 1 (from CS list) | Financial services | CS | Asked
Customer 2 | Healthcare | Sales | Asked
Customer 3 | Insurance | CS | Asked

## Rep Assets
Rep-ready assets
Track if assets are used in deals.
Asset | For | Built from | Status | Times used in deals
Industry one-pager: banking | MDR + AE | Webinar + case study | To do | 0
Industry one-pager: insurance | MDR + AE | Case study | To do | 0
Industry one-pager: healthcare | MDR + AE | Providence Health proof | To do | 0
Limina vs DIY comparison | AE | Product + customers | To do | 0
Email snippets with proof | MDR | Case studies | To do | 0
2-minute webinar cuts | MDR | Webinars | To do | 0
Security + deployment FAQ | CISO conversations | Product + security | To do | 0

## Hand-off Rules
Demand Gen ⇄ MDR hand-off rules
Agree in month 1, review every quarter.
Trigger | What happens | Owner | Time
Demo or pricing request | Instant alert; MDR replies | MDR | Within 1 business hour
Lead score 60+ (MQL) | MDR task with context note | Durva → MDR | Same day
Webinar attended | Attendee list + questions in HubSpot | Durva | Within 2 hrs
Webinar attended | Personal follow-up | MDR | Within 24 hrs
Account score 60+ | Account worked this week | MDR | This week
Event badge scan | Tagged by tier, follow-up | Durva → MDR | Within 48 hrs
Meeting held, not qualified | Back to nurture with reason | MDR → Durva | Same week
MDR hears a new objection | Shared in weekly sync | MDR → Durva | Weekly

## KPI Dashboard
Monthly KPI dashboard
Yellow = actuals to enter. Targets are SAMPLE. Rates calculate.
Metric | Dec | Jan | Feb | Mar | Apr | May | 6-mo total
Net-new leads (target) | 120 | 160 | 200 | 240 | 240 | 240
Net-new leads (actual)
MQLs (target) | 30 | 40 | 50 | 60 | 60 | 60
MQLs (actual)
Meetings (target) | 8 | 12 | 15 | 18 | 18 | 19
Meetings (actual)
Opportunities (target) | 2 | 3 | 4 | 5 | 5 | 5
Opportunities (actual)
Lead → MQL rate (actual)
MQL → meeting rate (actual)
Meeting → opportunity rate (actual)

## UTM Builder
UTM builder
Fill the yellow cells; the tracked URL builds itself.
Page URL | Source | Medium | Campaign | Content | Tracked URL
https://www.getlimina.ai/en | linkedin | paid-social | 2027-q1_webinar_governing-every-prompt | ad-a
https://www.getlimina.ai/en | email | nurture | 2027-q1_guide_ai-training-data | email-2
https://durvathakkar.com/limina/abm/?a=manulife | linkedin | abm | 2027-q1_abm-tier1 | manulife